## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2185-swen-261-04-d damns
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | SP; 3/31; Pass
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | SP; 3/31; Pass
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. |  | SP; 3/31; Pass
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  | SP; 3/31; Pass
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  | SP; 3/31; Pass
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  | SP; 3/31; Pass
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. |  | SP; 3/31; Pass
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | SP; 3/31; Pass
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | SP; 3/31; Pass
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | SP; 3/31; Pass
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | SP; 3/31; Pass
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | SP; 3/31; Pass
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | SP; 3/31; Pass
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | SP; 3/31; Pass
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | SP; 3/31; Pass
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | SP; 3/31; Pass
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | SP; 3/31; Pass
As a Player, I want to move a selected piece so that I May move to an unoccupied spot. | GIVEN there is an empty space in front me WHEN I am selected to move forward THEN I expect to move forward. |  |  |  | SP; 3/31; Pass
| GIVEN there is a piece in front of me or its the end of board WHEN I am selected to move forward THEN I expect to not move. |  |  |  | SP; 3/31; Pass
| GIVEN I am a king, and there is an empty space in front of me WHEN I am selected to move forward THEN I expect to move forward. |  |  |  | SP; 3/31; Pass
| GIVEN I am a king, and there is an empty space behind me WHEN I am selected to move backward THEN I expect to move backward. |  |  |  | SP; 3/31; Pass
| GIVEN I am a king, there is a piece in front of me or its the end of board WHEN I am selected to move forward THEN I expect to not move. |  |  |  | SP; 3/31; Pass
| GIVEN I am a king, there is a piece behind me or its the end of board WHEN I am selected to move backward THEN I expect to not move. |  |  |  | SP; 3/31; Pass
As a Player, I want to be able to capture my opponent's checkers so I can progess in the game | GIVEN I jump one of my pieces over an opponent's piece WHEN I have the piece selected THEN I capture the opponet's piece and remove it from the board |  |  |  | SP; 3/31; Pass
| GIVEN a piece of my has been captured WHEN it is a valid capture THEN my piece gets removed from the board. |  |  |  | SP; 3/31; Pass
As a Player, I want to king my checkers so that I can move them in any direction on the board. | GIVEN I am a piece WHEN I reach the end of the board THEN I expect to become a King. |  |  |  | SP; 3/31; Pass
| GIVEN I am a King WHEN I reach the end of the board THEN I expect to remain a King. |  |  |  | SP; 3/31; Pass
| Given I am a piece when I reach the end of the board then I expect my turn to end. |  |  |  | SP; 3/31; Pass
As a Player, I want to jump over my opponent's checkers so I can capture them. | Given I can make a jump When it is my turn, then I expect to only be able to make that move.
| Given I can make multiple jumps When it is my turn Then I expect to able to choose which jump to make |  |  |  | SP; 3/31; Pass
| Given I have jumped and can jump again When I have completed my jump Then I expect it to remain my turn and have to make that jump. |  |  |  | SP; 3/31; Pass
As a Player, I want to know if I win so I may win the game. | GIVEN My opponent can not make any moves when it is my turn then I have reached the win condition.
As a Player, I want the game to end, so there is a clear winner for each game. | GIVEN I have no pieces WHEN it becomes my turn THEN I expect to lose the game.
GIVEN I can not make any legal moves WHEN it becomes my turn THEN I expect to lose the game.
As a Player, I would like to be able to resign from a match so tha game can end early.
As a player I want to be able to request a rematch so that I can play another match.